## Overview
OrangeHRM Buzz — AI-Assisted QA Pipeline
Implementation summary per milestone — Senior QC review copy
Milestone | Input | Skill Used (version) | Output(s) | How It Was Implemented | Key QC Decisions / Corrections | Prompts Sent | Status
1. PRD Generation | Application URL | prd-generation (v1.0) | docs/PRD.md | Claude Code navigated the live OrangeHRM demo read-only via Playwright MCP, inventoried all 12 modules, and produced a fixed 15-section PRD. Buzz was documented as the detailed-scope module for Milestone 2 without being deep-dived, per the skill's generic scope-handling design. | QC review found Section 5 (Navigation) listed sub-nav items that never got a corresponding FR in Section 7. A correction pass added explicit addendum lines so every observed label is either covered by an FR or explicitly marked as not deep-inspected — no invented detail. | 1 main + 1 correction | Complete
2. UI Exploration | URL + PRD.md + scope = Buzz | ui-exploration (v2.0) | docs/exploration-findings.md | Deep-dived Buzz against the PRD's Section 6 as a map. Applied a defined Interaction Policy: safe/reversible actions (filters, Like→Unlike, expand/collapse) were exercised and confirmed reversed; content-creating actions (posting, commenting) were explicitly excluded since this is a shared public demo instance, and logged as such rather than silently skipped. | Corrected a PRD error found during exploration (Topbar 'hamburger' control was actually a Help button to an external site). Partially resolved BR-005 (edit/delete permission pattern) through live observation. | 1 main + 1 evidence cleanup | Complete
3. Test Design | URL + PRD.md + exploration-findings.md | test-design (v3.0) | test-design/test-design.csv (27 cases) | Generated a traceable test suite from the PRD and exploration findings only — no invented expected results. Positive, Negative, Edge, and Security cases included in proportion to what was actually evidenced. Two QC-only columns (Valid in Scope, Needs Automation) were left blank by design. | Schema was revised twice on QC lead's request: from 15 columns down to 12 (Requirement ID / Source / Comments removed for a simpler review sheet). After manual review, 6 of the original 'Needs Automation = Yes' hypothesis cases were changed to 'No' because automating them would post permanent content to the shared public demo on every run. | 1 main (run twice for schema change) | Complete
4. Test Execution | URL + PRD + exploration + reviewed CSV (Valid in Scope = Yes) | test-execution (v1.0) | execution/execution-report.html + 34 evidence screenshots | Executed the 20 directly-executable cases live via Playwright MCP with screenshot evidence per step. The 7 content-creating hypothesis cases were marked BLOCKED per the Interaction Policy rather than attempted. Every state-changing action (Likes, toggles) was reversed and the reversal confirmed before moving to the next case. The suite was later re-run in full from a clean state (results genuinely changed between runs, as expected on a live shared demo), and DEFECT-002 was separately investigated with a targeted re-verification before being withdrawn. Final result: 16 PASS, 2 PASS with documented deviation, 1 FAIL, 8 BLOCKED. | Formally raised DEFECT-001 (Share Video 'Share' button not disabled with an empty URL field, unlike Share Photos) - confirmed across both runs, remains open. On the full re-run, DEFECT-002 (Like/Unlike toggle) was initially raised as a new defect, then investigated via a targeted re-verification: the original attempt had clicked a display-only stats icon, not the real Like control - confirmed by network-request evidence (POST/DELETE returning 200 on the real control). DEFECT-002 was withdrawn as a test-targeting error, not a product defect; the original finding was kept in the report as an audit trail rather than deleted. Self-detected and corrected two accidental mis-clicks caused by a duplicate element ID, documenting them as tooling issues rather than app defects. On 2026-09-28, a QC-authorized live check (BUZZ-TC-024) found that clicking Share with an empty Video URL fires zero network requests and creates no post - the button stays enabled, but no invalid data is ever actually submitted. DEFECT-001 was reclassified from a confirmed functional defect to a UX inconsistency (the two Share dialogs use different but individually valid client-side validation patterns). The original finding was kept in the report for audit, not deleted. | 3 (initial execution + full re-run + DEFECT-002 targeted re-verification) | Complete - 23 PASS, 2 PASS†, 1 FAIL, 1 BLOCKED (TC-014 tooling only), 0 confirmed functional defects (DEFECT-001 reclassified 2026-09-28). BUZZ-TC-021-026 reclassified from policy-BLOCKED to PASS on 2026-09-28. BUZZ-TC-027 (cross-account Edit Post enforcement) formally RESOLVED on 2026-09-28 - a QC-authorized live check with a temporary second account confirmed the server rejects cross-account edits (HTTP 403), independent of the UI hiding the Edit option. This closes every originally-BLOCKED case except TC-014, which is a tooling limitation, not a policy exclusion.
5. Playwright Automation | URL + PRD + exploration + CSV (Needs Automation = Yes, 15 cases) + Milestone 4 execution report | playwright-automation (v3.2) | automation/tests/*.spec.ts + automation/reports/automation-execution-report.html + healing-log.md | Built a real Playwright (@playwright/test) suite for all 15 approved cases, organized by Page Object Model (BuzzPage, LoginPage) with shared fixtures. Read Milestone 4's locator-hazard findings first (duplicate heart-svg id, photo overlay div, non-disabling Share Video button) so scripts used correct locators from the start. DEFECT-001 was automated as an inverted-assertion regression probe (checks only the button's disabled state, never clicks Share) rather than an ordinary failing test. Tests were tagged by scheduling tier (read-only / state-changing / regression-probe) given the shared public demo. | 3 genuine automation bugs found and healed (H-01 to H-03: a crashed write-guard, a hidden vs. visible element mismatch, an over-strict DOM-removal check) - none were product or environment issues. One real environmental-drift bug caught and fixed before it could cause a wrong result (H-04: the shared demo's date format varies between sessions; the parser now reads the app's configured format at runtime instead of assuming one). One QC-approved test-design correction (C-01: TC-020's expected result was based on a misread of Milestone 4 evidence - both sort filters actually use the same tie-break key, not different ones - CSV corrected with reasoning logged). One QC-confirmed reconciliation, not a defect (R-01: TC-010's own-post menu item order set to match observed evidence). Credential-leak grep verified clean (password: 0/80 files; the 16 'username' matches were confirmed to be the unrelated 'Admin' role label, not the credential value). | 1 main + 1 test-design correction follow-up (TC-020) | Complete

## Deliverables Map
Deliverables Checklist (per original task brief)
Ref | Deliverable | File / Location | Status
a | Excel summary of milestone implementation | This file | Complete
b | Flowchart/sequence diagram (HTML) | diagrams/pipeline-flowchart.html | Complete
c | PRD md file | docs/PRD.md | Complete
d | Exploration md file | docs/exploration-findings.md | Complete
e | Test design CSV file | test-design/test-design.csv | Complete
f | Agent execution HTML report | execution/execution-report.html | Complete
g | Automation scripts + execution report + healing docs | automation/tests/, automation/reports/automation-execution-report.html, automation/reports/healing-log.md | Complete

## Reusable Skills
Reusable Skills Library (.claude/skills/)
Skill | Version | Purpose | Generic / Reusable Design
prd-generation | 1.0 | Generate a structured PRD for any web application from live, read-only observation. | Detailed-scope module (e.g. Buzz) is a per-run parameter, not hardcoded — the same skill works unmodified on a different app or module.
ui-exploration | 2.0 | Deep-dive a designated module's UI against a prior PRD, with a defined safety policy for shared/public environments. | Interaction Policy and scope module are both parameters; the skill has no project-specific detail baked in.
test-design | 3.0 | Turn a PRD + exploration findings into a traceable test-case CSV with QC-only review columns. | Column schema, coverage rules, and QC-field handling are all general-purpose; schema was revised once at QC lead's request without touching the methodology.
test-execution | 1.0 | Execute only QC-approved cases live, with PASS/PASS†/FAIL/BLOCKED classification and formal defect reporting. | Carries the ui-exploration skill's Interaction Policy forward automatically; not tied to this project's specific test cases.
playwright-automation | 3.2 | Convert 'Needs Automation = Yes' cases into real Playwright scripts, with healing-vs-defect-vs-drift diagnosis and regression probes for confirmed defects. | Regression-probe and three-way-diagnosis patterns apply to any project's automation phase, not just this one.

## Milestone 5 Detail
Milestone 5 — Automation Run Detail
Final run results (by scheduling tier)
Tier | Tests | Result
Read-only | 13 | 12 PASS, 1 BLOCKED (TC-020 was blocked pending correction; now PASS after C-01 fix)
State-changing | 1 (TC-008, Like/Unlike) | PASS. Exactly 1 Like + 1 Unlike sent; cleanup confirmed original state restored.
Regression probe | 1 (TC-019, DEFECT-001) | PASS = defect still present (button-enabled state, unchanged fact). Reclassified 2026-09-28: a live QC-authorized check found the empty-URL submission is actually blocked client-side (0 network requests, no post created) - DEFECT-001 is now a UX inconsistency, not a confirmed functional defect. Documentation updated; the probe itself was not re-run.
Healing & correction log
ID | Test(s) | Type | Summary
H-01 | TC-008 | Automation bug | A write-guard meant to block accidental posting crashed instead of blocking cleanly. Fixed; confirmed no request reached the server.
H-02 | TC-007 | Automation bug | Test targeted a hidden Read More link instead of the visible one. Locator corrected.
H-03 | TC-007 | Automation bug | Test checked for DOM removal; app only hides the element (still 'disappears' to a user). Assertion mechanism corrected, not the intent.
H-04 | TC-002, TC-003, TC-020 | Environmental drift (caught pre-emptively) | Shared demo's date format varies between sessions (Y-d-m vs Y-m-d observed). Parser now reads the app's configured format at runtime; an unparseable timestamp fails the test rather than silently mis-ordering.
C-01 | TC-020 | QC-approved test-design correction | Original expected result compared two posts with different Like counts and called it a 'tie' - a misreading, not an execution outcome. Corrected with reasoning logged; QC approved.
R-01 | TC-010 | QC-confirmed reconciliation (not a defect) | CSV listed 'Edit Post'/'Delete Post' with no stated order. Test set to match the order observed in Milestone 4 evidence (Delete Post first). QC confirmed.
Credential-leak verification
Password value: 0 matches across 80 files scanned. 'Username' string matched 16 times, all confirmed to be the unrelated 'Admin' role label appearing elsewhere in the app - not the credential in a leaked context.